## README
Last Update | 2019-10-16
Author | Daniel Kwong, Rahul Nair, Sandy Tsan, Tyler Ortiz, Jeremy Taraba
Email | dkwon014@ucr.edu, rnair005@ucr.edu, stsan003@ucr.edu, torti006@ucr.edu, jtara006@ucr.edu
Description | Our web-app, Piggy Bank, helps users financial with budgetting and saving as much as possible.
Summary / Requirements | This spreadsheet serves two purposes: (1) for your team to track progress during your sprints, and (2) as a record of what user stories were implemented, in which tasks, and by whom. For (1), if you prefer to use an alternate tool to track progress as you go (e.g., Trello), that is fine. However, for (2), it is critical that you keep the "Product Backlog" and "Archives" up to date, at least at the end of each sprint. Also, note that if the number of estimated points for a story ends up being very inaccurate (i.e., if the user story took much more or much less effort than expected), please update the story points estimate and give a comment explaining the adjustment.
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means to be "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Perform task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
3 | Google Registration | As an interested user, I want to be able to quickly sign in using my Google Account instead of using the routine sign in. | 1 | 5 | firebase authentication
6 | Expenses | As a user, I want to be able to access my expenses | 1
7 | Wireframe | As a user, I want a coherent layout that is intuitive and aesthetic | 1
4 | Navigation Bar | As a user, I want to see where I am in the website when I'm accessing it | 1
1 | Registration | As an unregistered customer who is interested in the app, I want to register an account so that I can login the app | 1 | 4 | firebase authentication
2 | Login/Logout | As a registered user, I want to login my account with user name and password, and logout my account to end the session | 1 | 3 | firebase authentication
| 2FA | As a user, I do not want unwarranted access to my account. | 2 | 10 | captcha lib.
8 | Home Page | As a user, we want a general homepage that we can use to acess other elements of the app | 2 | 10 | isn't this a navigation bar?
| Data Analytics | As a user of the web app, I want to be able to see my spendings through organized, aesthetic graphs and analytics | 1 | 3 | not sure maybe graphQL
| Savings/Debt Calculator | As a user of the web app, I want to be able to accurately calculate how much I need to save without having to go through the pain of calculating everything myself | 2 | 6 | might need to do from scratch
| In App Calculator | As a user of the web app, I want to do all of my work in one space and not have to switch between two apps | 2 | 7 | moon.js
| Spending Log | As a user, I want to be able to log my spendings | 2 | 7
| Budget | As a user I want to be able to set a budget for the month | 2 | 9
| Notification | As a registered user, I want to be notified of my progress in spending and saving money. | 2 | 8 | notification library (push.js)
| Disp. Exchange rate | As a foreign user, I would like to know up-to-date exchange rates for my country. | 2 | 12 | probably some API
| Spending Warnings | As an interested user, I want to be able to set boundaries and limitations on my spending. | 1 | 9 | javascript alerts
| Spending Cat. | As a registered user, I would like to see the different categories of my spending on the website | 3 | 2 | react components?
| Total |  | 27

## Archives
Sprint ID | Scrum Master | Tasks Completed | Tested/Verified by
1 | Daniel Kwong | Task 1: Build Log in/sign up page | Daniel Kwong
1 | Daniel Kwong | Task 2: build sign up page | Daniel Kwong
1 | Daniel Kwong | Task 3: Home tab | Rahul Nair
1 | Daniel Kwong | Task 4: Expenses Tab | Rahul Nair
2 | Daniel Kwong | Task 14: Budget | Daniel Kwong
2 | Daniel Kwong | Task 15: Spending Categories | Daniel Kwong
2 | Daniel Kwong | Task 11: In App Calculator | Daniel Kwong
3 | Daniel Kwong | Task 17: Restructure Expenses code | Tyler Ortiz
3 | Daniel Kwong | Task 18: Disp. Exchange Rate | Rahul Nair
3 | Daniel Kwong | Task 16: Savings/Debt Calculator | Daniel Kwong, Rahul Nair
3 | Daniel Kwong | Task 19: Navbar | Daniel Kwong, Rahul Nair
3 | Daniel Kwong | Task 20: 2FA | Daniel Kwong, Rahul Nair
3 | Daniel Kwong

## Task Board
To Do (Sprint Backlog) | In Progress | Testing | Done
Notifications |  |  | Task 15: Spending Categories (Rahul Nair and Daniel Kwong)
Page Routing/NavBar |  |  | Task 14: Budget(Rahul and Daniel Kwong)
Task 11: In App Calculator (Sandy)
Task 13: Spending Log(Tyler Ortiz, Daniel Kwong, and Rahul Nair)
Task 17: Restructure Expenses code(Tyler, Daniel Kwong)
Task 18: Disp. Exchange Rate (Daniel Kwong)
Task 16: Savings/Debt Calculator (Sandy, Daniel Kwong)
Task 10: Data Analytics (Jeremy, Rahul Nair)

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 27 | 0 | 0 | 27 | 27
1 | 27 | 7 | 4 | 23 | 20.25
2 | 27 | 7 | 14 | 13 | 13.5
3 | 27 | 0 | 14 | 13 | 6.75